## MIS Reconstruction Plan
MIS RECONSTRUCTION PLAN — APPROVAL SHEET
Instructions: Review each row. In column H mark: ✅ YES ¦ ❌ NO ¦ ⏸ LATER
# | Item / File | Category | Action | Priority | Why / What it does | Effect if Approved | APPROVE? (YES/NO/LATER) | Your Notes
── SECTION 1: DELETE – Frontend Pages (not needed for small team) ──
1 | RightSidebar.jsx | Frontend – Nav | DELETE | HIGH | 80px rail with 13 quick-action buttons. Duplicates left sidebar. Confusing on mobile. | Save 216 lines. Move 3 key actions to top navbar.
2 | FlowBuilderPage.jsx + 8 flow components | Frontend – Pages | DELETE | HIGH | Visual workflow designer. Complex; team of 4 has no time to build/maintain flows. | Remove 9 files. Auto-stage logic replaces this.
3 | BankReconciliation.jsx | Frontend – Pages | DELETE | HIGH | Bank statement matching. Enterprise feature. Wrong scale for 10 orders/day. | Remove 1 page (~18KB). Use simple cash/bank balance widget instead.
4 | TrialBalance.jsx | Frontend – Pages | DELETE | HIGH | Accounting trial balance. Needs a full Chart of Accounts setup. Not daily use. | Remove 1 page. Daily operations don't need this.
5 | OpeningBalance.jsx | Frontend – Pages | DELETE | MEDIUM | One-time data entry for accounting setup. Already done; no ongoing use. | Remove 1 page. Can be re-added later if needed.
6 | GmailAccounts.jsx + EmailCompose.jsx + EmailHistory.jsx | Frontend – Pages | DELETE | HIGH | Gmail OAuth integration. WhatsApp covers all customer communication. Gmail adds complexity. | Remove 3 pages. WhatsApp handles all notifications.
7 | WorkflowTemplates.jsx | Frontend – Pages | DELETE | MEDIUM | Template editor for order workflows. Replaced by fixed 8-stage pipeline. | Remove 1 page (~16KB). Fixed pipeline is simpler.
8 | CallLogs.jsx | Frontend – Pages | DELETE | MEDIUM | Phone call tracking. Not core to printing business ops. | Remove 1 page. Frees up sidebar space.
9 | DiaryUpload.jsx | Frontend – Pages | DELETE | MEDIUM | Daily work diary with image attachments. Not used in 30-min daily workflow. | Remove 1 page (~20KB).
10 | SopPage.jsx | Frontend – Pages | DELETE | LOW | SOP management page (17KB). Replace with simple checklist widget on dashboard. | Remove dedicated page. Add 5-item daily checklist to dashboard instead.
11 | PurchaseOrder.jsx + purchaseOrder route | Frontend – Pages | DELETE | MEDIUM | Vendor PO management. Overkill at current scale. Use note field on vendor payment. | Remove 1 page + 1 backend route.
12 | UpiPayment.jsx (standalone page) | Frontend – Pages | DELETE | LOW | Dedicated UPI page. Better as dashboard quick-action modal. | Remove page; keep UPI collection as dashboard widget.
13 | addTransaction1.jsx (standalone) | Frontend – Pages | DELETE | MEDIUM | Transaction entry page. Replace with quick inline add from accounts view. | Remove 1 page (268 lines).
14 | AttendanceReport.jsx (one of two) | Frontend – Pages | DELETE | LOW | Duplicate attendance view. Keep AllAttandance.jsx, remove the report variant. | Remove 1 of 2 attendance pages.
15 | WhatsApp legacy pages (Baileys) – 4 files | Frontend – Pages | DELETE | HIGH | Unofficial QR-based WhatsApp Web integration. Fragile, can break any time. | Keep Cloud API WhatsApp only. Remove 4 legacy WhatsApp pages.
── SECTION 2: DELETE – Reports (17 → 3) ──
1 | allTransaction.jsx | Reports | DELETE | HIGH | One of 5 transaction report variants. Consolidate into 1 smart Collections report. | Remove 1 report. Replaced by new Collections report.
2 | allTransaction4D.jsx | Reports | DELETE | HIGH | Advanced 4D transaction view (284 lines). Rarely used by 4-person team. | Remove 1 report.
3 | agingReport.jsx | Reports | DELETE | MEDIUM | Accounts receivable aging. Useful for large teams; overkill for 10 orders/day. | Remove 1 report. Overdue orders visible on dashboard instead.
4 | allBills.jsx (current version) | Reports | REWRITE | HIGH | 879 lines with multi-view, export, modal. Merge into Collections report (simpler). | Rewrite as 150-line Collections tab with date filter + export.
5 | allDelivery.jsx | Reports | DELETE | MEDIUM | Separate delivery tracking report. Fold into Orders report with stage filter. | Remove 1 report. Orders report with 'Delivered' filter replaces this.
6 | priorityReport.jsx | Reports | DELETE | LOW | Priority master data table. Admin config; not daily use. | Remove 1 report.
7 | taskReport.jsx | Reports | DELETE | LOW | Task productivity tracking. Not relevant to 30-min daily workflow. | Remove 1 report.
8 | userReport.jsx | Reports | DELETE | LOW | User activity report. Admin-level; not operational need. | Remove 1 report.
9 | billUpdate.jsx | Reports | DELETE | MEDIUM | Bill status update page (167 lines). Move bill paid toggle into Orders report. | Remove 1 page. Mark paid from Orders report inline.
── SECTION 3: REWRITE – Core Components ──
1 | Dashboard.jsx (754 lines → ~200 lines) | Frontend – Pages | REWRITE | HIGH | Current: 11 KPI cards, 6 resizable panels, customization drawer. Way too complex. | New: 5 KPIs (Today orders, Ready, Overdue, Collections today, Pending payment), Needs-Attention list, Pipeline stage counts.
2 | addOrder1.jsx (1,726 lines → ~180 lines) | Frontend – Pages | REWRITE | HIGH | Current order form has vendor assignments, task groups, Drive integration, 15+ fields. Too slow. | New: 6 fields only – Customer, Item/Qty/Rate table, Due Date, Priority, Advance Paid. <2 min to create order.
3 | OrderUpdate.jsx (710 lines → ~150 lines) | Frontend – Pages | REWRITE | HIGH | Order edit page is too complex. Most edits are: change due date, add note, fix amount. | New: read-only view + edit due date, priority, items. Stage advance from Kanban only.
4 | Sidebar.jsx (288 lines → ~80 lines) | Frontend – Nav | REWRITE | HIGH | Current: 30+ menu items across 8 groups with role filtering logic. | New: 6 items flat list – Dashboard, Orders, Customers, Accounts, Reports, Settings.
5 | sidebarMenu.jsx constant file | Frontend – Nav | DELETE | HIGH | 148-line menu config file becomes unnecessary after sidebar rewrite. | Delete file; menu items go inline in new Sidebar.jsx.
6 | TopNavbar.jsx | Frontend – Nav | REFACTOR | MEDIUM | Add 3 quick-action buttons here to replace right sidebar functionality. | + New Order button + Notifications bell + Profile. Right sidebar eliminated.
7 | Footer.jsx (mobile nav) | Frontend – Nav | REWRITE | LOW | Current 5 tabs: Home, Orders, Tasks, Bills, Chat. Tasks and Chat tabs unused. | New 4 tabs: Dashboard, Orders, + New Order, Accounts.
8 | App.jsx (66 routes → ~25 routes) | Frontend – Core | REFACTOR | HIGH | Remove ~40 routes for deleted pages. Keeps routing lean. | Smaller bundle; faster initial load.
9 | DayBook.jsx (1,066 lines) | Frontend – Pages | REWRITE | HIGH | Complex multi-tab daily accounting. Replace with simple Income/Expense log. | New: date-filtered list of income (order payments) + expenses. 150 lines.
── SECTION 4: KEEP & REBUILD – 3 Core Reports ──
1 | Orders Report (new – replaces allOrder, allDelivery, AllOrderTableView) | Reports | REWRITE | HIGH | Single report: date range + stage filter + customer filter. Export Excel. | One report covers all order tracking needs.
2 | Collections Report (new – replaces allBills, paymentReport, allTransaction) | Reports | REWRITE | HIGH | Single report: income vs expenses by date range. Mark bill paid inline. Export Excel. | One report covers all money tracking.
3 | customerReport.jsx (keep, minor cleanup) | Reports | REFACTOR | LOW | Customer master table. Already clean (~303 lines). Minor UI polish only. | Keep as-is with small style fixes.
── SECTION 5: ADD – Backend Automation ──
1 | Auto WhatsApp on stage change | Backend – Automation | ADD | HIGH | When order moves to approved/design/ready/delivered, auto-send WhatsApp to customer. | Zero human effort for status updates. Customer stays informed automatically.
2 | Auto payment reminder (daily cron) | Backend – Automation | ADD | HIGH | Daily 10am: find delivered but unpaid orders older than 2 days → send WhatsApp reminder. | Payment follow-up happens automatically. No manual chasing.
3 | Auto daily summary to owner (7pm) | Backend – Automation | ADD | MEDIUM | Daily 7pm: aggregate today's new orders, completions, collections → WhatsApp to owner. | Owner sees day summary on phone without opening dashboard.
4 | Auto vendor assignment on order create | Backend – Automation | ADD | MEDIUM | When order created, auto-assign vendor steps based on item type preference (logic already exists in vendorService.js, just not wired). | Vendor assignment becomes zero-click. Saves 3-5 min per order.
── SECTION 6: BACKEND CLEANUP ──
1 | Remove Status[] array from Order model (use stage field only) | Backend – Model | REFACTOR | HIGH | Order has both Status[] (legacy array) and stage (string). Confusing; both populated. | Single source of truth for order stage. Simpler queries.
2 | Delete Enquiry collection (use Orders with stage='enquiry') | Backend – Model | DELETE | MEDIUM | Enquiry table barely used. All enquiries already stored as Orders with stage=enquiry. | Remove 1 collection. Simpler data model.
3 | Remove Baileys backend (baileysService.js, Baileys.js route, baileysAuthState model) | Backend – Routes | DELETE | HIGH | Unofficial WhatsApp Web integration. Can break any time Meta updates. Duplicate of Cloud API. | Remove 3 files + 1 model. Cloud API is stable and official.
4 | Remove Flow/FlowSession backend (flowController, flowEngineService, flow routes) | Backend – Routes | DELETE | HIGH | Visual workflow engine. Over-engineered for 4-person team. Auto-stage logic replaces it. | Remove 4 files + 2 models.
5 | Remove Gmail backend (Gmail.js route, gmailAccount model, gmailService.js) | Backend – Routes | DELETE | MEDIUM | Gmail OAuth integration. WhatsApp covers all customer communication. | Remove 3 files + 1 model.
6 | Remove CallLogs backend route + model | Backend – Routes | DELETE | MEDIUM | Call tracking not core to printing ops. | Remove 1 route + 1 model.
7 | Standardise vendor reference (always vendorUuid, remove vendorCustomerUuid) | Backend – Model | REFACTOR | MEDIUM | Orders use both vendorUuid and vendorCustomerUuid inconsistently. | Cleaner queries; removes join confusion.
8 | Simplify createOrder function (268 lines, 15 concerns) | Backend – Service | REFACTOR | MEDIUM | One function handles: order creation, item normalization, vendor assignment, workflow, tasks, Drive file. Hard to debug. | Split into 5 focused functions. Easier to maintain.
── SECTION 7: SIMPLIFY – Accounts ──
1 | Replace double-entry Day Book with Income/Expense Log | Accounts | REWRITE | HIGH | Double-entry (Dr = Cr invariant) is accountant-level. Team needs: money in, money out, balance. | Simple list: Date ¦ Type ¦ Amount ¦ Category ¦ Note ¦ Order#. No journal entries.
2 | Remove Chart of Accounts (Accounts model) from daily UI | Accounts | SIMPLIFY | MEDIUM | CoA is needed for proper accounting but not for daily 30-min workflow. | Keep model in DB but hide from daily UI. Show only in Settings > Admin.
── SECTION 8: KEEP (no changes) ──
1 | OrderKanban.jsx + OrderBoard + OrderCard + OrderColumn | Frontend – Pages | KEEP | – | Kanban is the right UI for this workflow. Minor card simplification only. | Keep. Small card cleanup: remove assignee avatar, simplify drag-drop.
2 | WhatsApp Cloud API pages (WhatsAppCloud*.jsx) | Frontend – Pages | KEEP | – | Official Meta API integration. Keep for broadcast, templates, catalog. | Keep all Cloud API WhatsApp pages.
3 | Customer CRUD (addCustomer.jsx, customerReport.jsx) | Frontend – Pages | KEEP | – | Core master data. Simple and clean already. | Keep as-is.
4 | Item master (addItem.jsx) | Frontend – Pages | KEEP | – | Product catalog. Needed for order creation. | Keep as-is.
5 | Authentication (login.jsx, Register.jsx, AuthContext) | Frontend – Core | KEEP | – | JWT auth works well. No changes needed. | Keep as-is.
6 | Socket.IO real-time updates (socket.js) | Backend – Core | KEEP | – | Real-time order updates across team. Valuable for 4-person team coordination. | Keep as-is.
7 | Cloudinary file upload | Backend – Core | KEEP | – | Design file storage. Still needed for order design files. | Keep as-is.
8 | PaymentFollowup.jsx | Frontend – Pages | KEEP | – | Payment follow-up list. Useful. Will be supplemented by auto-reminder (Section 5). | Keep. Auto-reminders will reduce manual use.

## Legend & Instructions
LEGEND
Column H – APPROVE?
✅ YES | Approve this change — implement it
❌ NO | Do NOT make this change — keep as-is
⏸ LATER | Skip for now, revisit later
ACTION COLOURS
DELETE (red) | File / feature will be completely removed
REWRITE (orange) | File rebuilt from scratch (simpler version)
REFACTOR (yellow) | Existing file cleaned up / improved
ADD (green) | New feature / automation added
KEEP (blue) | No change — left as-is
SIMPLIFY (purple) | Reduced in scope / hidden from daily UI
PRIORITY
HIGH | Core to 30-min daily workflow — do first
MEDIUM | Improves system — do second pass
LOW | Nice to have — do last
HOW TO USE
Step 1 | Read each row carefully
Step 2 | In Column H type YES / NO / LATER for each item
Step 3 | Add any notes in Column I
Step 4 | Share the filled Excel back for implementation

## Summary Counts
Category | Count
Pages to DELETE | 17
Reports to DELETE | 9
Components to REWRITE | 8
Backend routes/models to DELETE | 6
Automation features to ADD | 4
Items to KEEP unchanged | 7
Total frontend files touched | ~60
Estimated lines removed | ~15,000
Estimated lines remaining | ~5,000
Expected daily dashboard time | ≤30 min
New order creation time | <2 min
Manual WhatsApp messages/day | 0 (automated)