## 1. Delete Dead Code
# | File / Feature | Area | Why Remove | Approve | Priority
▶ FE Pages
1 | Pages/home.jsx *** UNROUTED — dead code *** | Home/Landing | /home route serves Dashboard.jsx — home.jsx is not connected to ANY route. 181 lines with 2-sec artificial setTimeout, mixes attendance+tasks+orders. DELETE; Dashboard.jsx becomes the single home screen. |  | High
2 | Components/RightSidebar.jsx | Navigation | Duplicates left nav; confusing rail buttons — move 5 actions to top navbar instead. |  | High
3 | Pages/FlowBuilderPage.jsx | Automation | Visual flow builder too complex; team of 4 has no time to design automations. |  | High
4 | Pages/BankReconciliation.jsx | Accounts | Enterprise feature; wrong scale for 10 orders/day. |  | High
5 | Pages/TrialBalance.jsx | Accounts | Accountant-level tool; not needed daily. |  | High
6 | Pages/OpeningBalance.jsx | Accounts | One-time setup page; not needed after initial entry. |  | Medium
7 | Pages/GmailAccounts.jsx | Email | WhatsApp covers all customer communication; Gmail adds complexity. |  | High
8 | Pages/EmailCompose.jsx | Email | Same — consolidated into WhatsApp. |  | High
9 | Pages/EmailHistory.jsx | Email | Same — consolidated into WhatsApp. |  | High
10 | Pages/CallLogs.jsx | CRM | Not core to printing business ops; rarely used. |  | Medium
11 | Pages/DiaryUpload.jsx | Misc | Non-essential daily upload feature. |  | Medium
12 | Pages/SopPage.jsx | Ops | Replace with simple daily checklist embedded in dashboard. |  | Medium
13 | Pages/WorkflowTemplates.jsx | Automation | Replaced by fixed pipeline; team doesn't need custom workflow editing. |  | High
14 | Pages/UpiPayment.jsx (standalone) | Accounts | Merge UPI collection into dashboard quick-action widget instead. |  | Medium
15 | Pages/addTransaction1.jsx | Accounts | Replace with inline quick-add in simple accounts log. |  | Medium
16 | Pages/AttendanceReport.jsx (duplicate) | HR | Keep AllAttandance.jsx; remove duplicate report. |  | Low
17 | Pages/purchaseOrder.jsx | Procurement | Overkill at current scale; add note on vendor payment instead. |  | Medium
▶ Legacy WhatsApp (Baileys)
18 | Pages/WhatsApp*.jsx (all Baileys pages) | WhatsApp | Unofficial QR-based; fragile; Cloud API replaces all of these. |  | High
19 | Components/whatsapp/ (legacy folder) | WhatsApp | All legacy WA components; superseded by whatsappCloud/ folder. |  | High
▶ Reports — consolidate 17 into 3
20 | Reports/allTransaction.jsx | Reports | 5 transaction views collapse into 1 smart Collections report. |  | High
21 | Reports/allTransaction4D.jsx | Reports | Same — fold into Collections report. |  | High
22 | Reports/allBills.jsx (879-line version) | Reports | Rebuild as simplified Bills tab inside Collections report. |  | High
23 | Reports/agingReport.jsx | Reports | Overkill; receivables aging not actionable daily for small team. |  | Medium
24 | Reports/priorityReport.jsx | Reports | Admin-level; low daily use. |  | Low
25 | Reports/taskReport.jsx | Reports | Tasks visible on dashboard; separate report not needed. |  | Low
26 | Reports/userReport.jsx | Reports | Admin-level; low daily use. |  | Low
27 | Reports/allDelivery.jsx | Reports | Fold delivery tracking into Orders report. |  | Medium
28 | Reports/billUpdate.jsx | Reports | Bill status updates happen from Kanban; standalone page redundant. |  | Medium
29 | Reports/paymentReport.jsx | Reports | Merge into Collections report. |  | Medium
▶ Backend routes + models to remove
30 | MISBackend/routes/Baileys.js | Backend | Remove with Baileys frontend. |  | High
31 | MISBackend/services/baileysService.js | Backend | Same. |  | High
32 | MISBackend/repositories/baileysAuthState.js | Backend | Same. |  | High
33 | MISBackend/routes/Gmail.js | Backend | Remove with Gmail frontend. |  | High
34 | MISBackend/routes/BankStatement.js | Backend | Remove with BankReconciliation frontend. |  | High
35 | MISBackend/routes/workflowTemplate.js | Backend | Remove with WorkflowTemplates frontend. |  | High
36 | MISBackend/routes/PurchaseOrder.js | Backend | Remove with purchaseOrder frontend. |  | Medium
37 | MISBackend/repositories/flow.js + flowSession.js | Backend | Remove with FlowBuilder frontend. |  | High

## 2. Rewrite & Simplify
# | File | Current Lines | Target Lines | Key Changes | Approve | Priority
▶ HOME / LANDING PAGE
1 | Pages/home.jsx → DELETE (see Sheet 1 row 1) | 181 | 0 | home.jsx is NOT the /home route — Dashboard.jsx is. home.jsx is dead code. After cleanup, ROUTES.HOME ('/home') continues to serve the new simplified Dashboard.jsx. No separate 'home' page needed. |  | High
▶ NAVIGATION
2 | Components/Sidebar.jsx | 288 | ~80 | 6 items flat list: Dashboard / Orders / Customers / Accounts / Reports / Settings (admin only). Remove all groups and collapsible sections. Delete sidebarMenu.jsx config file entirely. |  | High
3 | Components/TopNavbar.jsx | 100+ | ~80 | Add [+ New Order] primary button. Move 5 right-sidebar quick actions here. Remove right sidebar dependency. |  | High
4 | Components/Footer.jsx (mobile bottom nav) | 50 | ~40 | 4 tabs only: Dashboard / Orders / + New Order / Accounts. Remove Tasks and Chat tabs. |  | Medium
▶ DASHBOARD (= the /home route)
5 | Pages/Dashboard.jsx — serves ROUTES.HOME = '/home' | 754 | ~200 | This IS the home screen after login. New layout: 5 KPI tiles (Today Orders, Ready, Overdue, Collected ₹, Pending ₹) + 'Needs Attention' list (max 5 stuck/overdue orders with [Move] button) + Stage pipeline count bar. REMOVE: resizable panels, customization drawer, attendance section, user tasks section, design files widget. |  | High
6 | Components/dashboard/ (folder) | ~300 | ~80 | Keep SummaryCard + QuickActions only. Delete: CrmSidebarPanel, ActionList, RoleWidget, DesignFilesWidget. Simplify UpiCollectionSection to a single inline button. |  | High
▶ ORDER MANAGEMENT
7 | Pages/addOrder1.jsx | 1726 | ~180 | 6 fields only: Customer (autocomplete), Items/Qty/Rate table (max 5 rows), Due Date (default +3 days), Priority (Low/Normal/Urgent chip), Advance Paid (yes/no + amount). 2 save buttons: [Save as Enquiry] and [Save as Order]. REMOVE: vendor section (auto-assign on backend), task groups, Google Drive, date override, WA toggle (always auto-send). |  | High
8 | Pages/OrderUpdate.jsx | 710 | ~150 | Read-only order detail. Editable fields: due date, priority, items qty/rate, add note. Stage advance moves to Kanban board only. |  | High
9 | Pages/OrderKanban.jsx + Components/orders/OrderCard.jsx | ~300 | ~150 | Keep Kanban paradigm. Simpler card: #order · Customer ¦ Item summary ¦ Due: X days ¦ ₹ amount ¦ [→ Next Stage] button. 8 columns = full pipeline. Remove drag-drop; use [→ Stage] button only. |  | High
▶ ACCOUNTS (Simplify)
10 | Pages/DayBook.jsx | 1066 | ~120 | Replace double-entry complexity with Income/Expense log. Two tabs: Income (auto-created when order paid) ¦ Expenses (manual). Table: Date ¦ Type ¦ Amount ¦ Category ¦ Order# ¦ Note. Totals at top: Income ₹X — Expenses ₹Y = Profit ₹Z. |  | High
▶ REPORTS (Rebuild 17 → 3)
11 | Reports/allOrder.jsx → New: Orders Report | 712 | ~200 | Table + filters: date range, stage, customer. Columns: Order# ¦ Customer ¦ Items ¦ Amount ¦ Stage ¦ Due Date ¦ Assigned. Export Excel. Replaces: allOrder, AllOrderTableView, allDelivery. |  | High
12 | New file: Reports/collectionsReport.jsx | — | ~200 | Income + expenses by date. Summary: Total In ¦ Total Out ¦ Net. Replaces: allBills, allTransaction*, paymentReport. Export Excel. |  | High
13 | Reports/customerReport.jsx | 303 | ~150 | Minor cleanup: remove unused columns. Keep search, group filter, edit/delete. |  | Low
▶ BACKEND
14 | controllers/orderLifecycleController.js | ~200 | ~180 | Add auto-WhatsApp send after each stage change using existing whatsappCloudService.sendTemplate(). Reuse whatsappTemplates.js config. |  | High
15 | services/messageScheduler.js | ~150 | ~200 | Add two cron jobs: (a) daily 10am payment reminder for delivered-unpaid orders; (b) 7pm owner summary WhatsApp with today's stats. |  | High
16 | App.jsx (router) | 66 routes | ~35 routes | Remove routes for all deleted pages. Keep ~35 active routes. |  | High

## 3. Automation to Add
# | Feature | What It Does | Files to Change | Trigger | Approve | Priority
▶ WHATSAPP AUTO-MESSAGES (Backend — zero human action)
1 | Order confirmation WA | On order creation: auto-send 'Order #N received, amount Rs.X, due date Y' to customer. | orderService.js (create hook) | Order created |  | High
2 | Stage-change WA message | Auto-send WA to customer when order moves to: approved / design / ready / delivered. Messages defined in whatsappTemplates.js. | orderLifecycleController.js + whatsappTemplates.js | PATCH /stage |  | High
3 | Payment reminder WA | Daily 10am: find all delivered-unpaid orders older than 2 days. Send WA: 'Your order #N of Rs.X is pending payment.' | messageScheduler.js | Cron 10:00 |  | High
4 | Daily owner summary WA | 7pm every day: aggregate today's stats (new orders, stage moves, collections, overdue count). Send WhatsApp summary to owner's number (configured in BusinessOps). | messageScheduler.js | Cron 19:00 |  | High
5 | Enquiry follow-up WA | If enquiry stays in 'quoted' stage > 24h, auto-send follow-up message to customer. | messageScheduler.js | Cron daily 11:00 |  | Medium
▶ ORDER AUTOMATION (Backend)
6 | Auto vendor assignment | On order creation, auto-assign preferred vendor to each production step based on item type — no manual vendor selection needed. | orderService.js + vendorService.js (already exists, just not wired) | Order created |  | High
7 | Auto task creation | Auto-create designer task when order moves to 'design' stage. (Already partly built in orderLifecycleController — complete the wiring.) | orderLifecycleController.js | Stage = design |  | Medium
8 | SLA / stuck-order alert | Flag order in dashboard 'Needs Attention' section if it stays in the same stage > 2 days. | dashboardSummaryController.js + /api/dashboard/stuck-orders endpoint | Dashboard load |  | Medium
▶ ACCOUNTS AUTOMATION
9 | Auto income entry | When order is marked 'paid', auto-create income transaction. No manual journal entry needed. | orderLifecycleController.js + transactionService.js | Stage = paid |  | High
10 | Auto PDF invoice on delivery | When stage moves to 'delivered', auto-generate PDF invoice and attach to order record. | orderLifecycleController.js + InvoiceModal.jsx (existing) | Stage = delivered |  | Medium

## 4. DB & Backend Cleanup
# | Collection / Code | Action | Why | Approve | Priority
▶ MONGODB COLLECTIONS — REMOVE
1 | Enquiry collection | Delete | All enquiries now stored as Orders with stage=enquiry. Enquiry table is dead code. |  | High
2 | Flow + FlowSession | Delete | Removing flow builder frontend; collections unused. |  | High
3 | BaileysAuthState + BaileysMessage | Delete | Removing Baileys WhatsApp; collections unused. |  | High
4 | EmailHistory + GmailAccount | Delete | Removing Gmail integration. |  | High
5 | BankStatement | Delete | Removing bank reconciliation. |  | High
6 | PurchaseOrder | Delete | Removing purchase order module. |  | Medium
7 | CallLogs | Delete | Removing call logs page. |  | Medium
8 | DiaryDraft | Delete | Removing diary upload. |  | Medium
▶ ORDER MODEL — FIELD CLEANUP
9 | Order.Status[] (array field) | Remove | Legacy field; replaced by Order.stage (string). Every query must handle both — confusing and error-prone. |  | High
10 | Order.vendorCustomerUuid | Remove | Old FK; standardise to vendorUuid everywhere. |  | Medium
11 | Order.workflowSteps[] | Audit | Check if actively used; if fewer than 20% of orders have data, remove entirely. |  | Medium
▶ CODE QUALITY
12 | API naming: /GetOrderList, /GetDeliveredList | Rename to kebab-case | Inconsistent with REST conventions; rename to /orders, /delivered-orders. |  | Low
13 | Error response format inconsistency | Standardize | Mix of {success,message} and {status,message}; pick one schema and apply everywhere. |  | Low
14 | Hardcoded 'Sai' as default assignee | Remove | Replace with null or first available user; hardcoded names break on new installs. |  | Medium
15 | Pagination on /api/orders/all-data | Add | Missing pagination causes slow load; will get worse as order count grows. |  | High

## 5. UI-UX New Design Spec
Component | New Design Spec | Approve
/home route (= Dashboard.jsx) | After login, user lands on Dashboard.jsx served at ROUTES.HOME = '/home'. home.jsx (the unused file) is deleted. One home screen, no confusion.
Dashboard — KPI Row | 5 tiles in one row: Today Orders (blue) ¦ Ready to Deliver (green) ¦ Overdue (red, alert if >0) ¦ Collected Today Rs. (green) ¦ Pending Payment Rs. (orange). Tap any tile to filter.
Dashboard — Needs Attention | Max 5 items. Each shows: order# + customer + current stage + days stuck + [Move Stage] button. Red background if overdue. Yellow if 1-2 days late. Empty state message: All on track!
Dashboard — Stage Pipeline Bar | Horizontal row: Enquiry(n) > Quoted(n) > Approved(n) > Design(n) > Printing(n) > Post-Print(n) > Ready(n) > Delivered(n). Tap stage to filter Kanban.
Left Sidebar | 6 items ONLY: Dashboard ¦ Orders ¦ Customers ¦ Accounts ¦ Reports ¦ Settings (admin). Flat list, icon + label. No groups, no collapsible sections. Width 200px.
Top Navbar | Left: hamburger + logo. Center: page title. Right: [+ New Order] orange primary button + bell notification icon + user avatar.
Right Sidebar | DELETED — its 5 quick actions move to top navbar.
Mobile Bottom Nav | 4 tabs: Dashboard ¦ Orders ¦ + (add order, prominent) ¦ Accounts. Sticky bottom. Remove Tasks and Chat tabs.
Add Order Form | 6 fields: Customer (autocomplete search), Items+Qty+Rate inline table (max 5 rows), Due Date (datepicker, default today+3), Priority (Low/Normal/Urgent chip selector), Advance Paid (toggle yes/no + amount field). Bottom buttons: [Save as Enquiry] (grey outline) and [Save as Order] (primary orange).
Kanban Board | 8 columns (all pipeline stages). Card shows: #N Customer ¦ Item summary ¦ Due: X days ago/from now ¦ Rs. amount ¦ [Next Stage] button. Tap card = order detail modal. No drag-drop — stage buttons only.
Order Detail Modal | Header: order#, customer, created date (read-only). Editable: due date, priority, add note, items qty/rate. Bottom: stage history timeline. [Mark Paid] button (if stage=delivered). [Print Invoice] button.
Accounts Page | Two tabs: Income ¦ Expenses. Table: Date ¦ Category ¦ Amount ¦ Order# ¦ Note. Top summary bar: Income Rs.X — Expenses Rs.Y = Profit Rs.Z. [+ Add Expense] button. Income entries created automatically when order is paid.
Reports — Orders | Filters: Date Range + Stage dropdown + Customer search. Table: Order# ¦ Customer ¦ Items ¦ Amount ¦ Stage ¦ Due Date ¦ Assigned To. Export Excel button top-right.
Reports — Collections | Filters: Date Range + Type (Income/Expense). Summary row: Total In ¦ Total Out ¦ Net. Table: Date ¦ Type ¦ Category ¦ Amount ¦ Order# ¦ Note. Export Excel.
Notifications Bell | Dropdown list in top navbar: overdue orders, payment reminders, stage changes. Badge count. [Mark all read] button.
Colour Theme | Primary: #2C3E50 (dark navy). Accent/CTA: #E67E22 (orange). Success: #27AE60. Danger: #C0392B. Background: #F8F9FA. Cards: white + subtle shadow.
Typography & Spacing | Font: Inter or system-ui. Headings: 600 weight 16-20px. Body: 400 weight 14px. Captions: 12px grey. Card padding 16px. Table row height 44px. Mobile tap targets min 44px.

## 6. Execution Roadmap
Phase | Phase Name | Files Changed | Tasks | Est. Effort | Approve | Status
▶ Phase 1 — Delete
1 | Delete dead code | ~26 FE pages, ~12 BE routes, ~8 DB models | Delete home.jsx (unrouted). Remove Baileys, Gmail, FlowBuilder, BankReconciliation, TrialBalance, CallLogs, DiaryUpload, legacy WA pages/components, 14 reports, SopPage, WorkflowTemplates, PurchaseOrder. Update App.jsx routes. | 1-2 days |  | Pending
▶ Phase 2 — Navigation
2 | Rebuild Sidebar + Navbar + Footer | Sidebar.jsx, TopNavbar.jsx, Footer.jsx, delete sidebarMenu.jsx | Flat 6-item sidebar, top quick-action bar with [+ New Order], 4-tab mobile footer. | 0.5 day |  | Pending
▶ Phase 3 — Dashboard (= /home)
3 | Rebuild Dashboard.jsx (the /home route) | Dashboard.jsx, Components/dashboard/ folder | 5 KPI tiles + Needs Attention list + Stage pipeline bar. Remove resizable panels, customization drawer, attendance section, user tasks section. | 1 day |  | Pending
▶ Phase 4 — Order Forms
4 | Rebuild Add Order + Order Update | addOrder1.jsx, OrderUpdate.jsx | 6-field add order form. Simplified edit form (read-only + editable fields only). | 1 day |  | Pending
▶ Phase 5 — Kanban
5 | Simplify Kanban board | OrderKanban.jsx, OrderBoard.jsx, OrderCard.jsx | Simpler cards, [Next Stage] button, 8 columns, remove drag-drop. | 0.5 day |  | Pending
▶ Phase 6 — Reports
6 | Rebuild Reports (17 -> 3) | Reports/ folder | Orders Report, Collections Report (new file), Customer Report (minor cleanup). | 1 day |  | Pending
▶ Phase 7 — Accounts
7 | Simplify Accounts | Pages/DayBook.jsx, accounts backend routes | Replace double-entry DayBook with simple Income/Expense log. Two tabs. | 0.5 day |  | Pending
▶ Phase 8 — Backend Automation
8 | Add automation | orderLifecycleController.js, messageScheduler.js, whatsappTemplates.js, orderService.js | Auto WA on order creation + stage changes. Payment reminders cron (10am). Daily owner summary cron (7pm). Auto income entry on payment. | 1 day |  | Pending
▶ Phase 9 — DB Cleanup
9 | Clean DB models | repositories/ folder + migration script | Remove unused collections (Enquiry, Flow, Baileys, Gmail, BankStatement, PurchaseOrder, CallLogs, DiaryDraft). Remove Order.Status[] array. Add pagination to /api/orders/all-data. | 0.5 day |  | Pending
▶ Phase 10 — QA
10 | End-to-end testing | All changed files | Golden path: Create order (target <2 min) > advance stages > verify WA sent > mark paid > check collections report. Test mobile layout. Check role-based access. | 0.5 day |  | Pending